## Alpha by Title
Number | Title | Upload Date | Size
85 | 2018 Field Data/Biological Resources | 2019-10-30 | 5.79 MB
117a | 2019 Cultural Resource Surveys Clarification | 2020-01-31 | 2.58 MB
25a | 2019 Offshore Culture Resources Survey Data | 2019-10-30 | 85 KB
107 | Access Roads to Water Extraction Sites | 2019-01-11 | 95 KB
113a | Addendum to the Cultural Resources Summary Report | 2020-04-30 | 1.36 MB
71d | Additional Avoidance and Minimization Measures Suggested by Cooperating Agencies | 2020-07-23 | 352 KB
124 | Additional Project Simulation | 2019-07-26 | 634 KB
59a | Additional Throughput Option | 2019-10-30 | 279 KB
106 | Additional Water Quality Data | 2019-02-11 | 3.62 MB
9 | Air Quality Dispersion Modeling | 2020-01-31 | 3.31 MB
137 | Air Quality Dispersion Modeling | 2019-10-30 | 33.25 MB
141 | Air Quality Dispersion Modeling Deposition Input Details | 2019-10-30 | 2.85 MB
7 | Air Quality Emission Inventories | 2020-01-31 | 3.73 MB
12 | Air Quality Related Values | 2018-12-12 | 125 KB
41 | Airport Air Traffic Data | 2020-02-27 | 9 KB
154 | Alternate Newhalen River Crossing | 2020-01-31 | 839 KB
136 | Alternative 1 Airport Spur Road Land Availability | 2019-09-20 | 273 KB
168 | Alternative 3 Base Case Optimizations | 2020-07-23 | 4.9 MB
120 | Alternative Alignment for Natural Gas Pipeline | 2019-10-30 | 3.07 MB
121 | Alternative ferry route and natural gas pipeline crossing alignment across Iliamna Lake | 2019-06-18 | 13.2 MB
94 | Alternative Option to Develop Pebble East Using Underground Mining | 2019-10-30 | 3.2 MB
127 | Alternative Road Alignment to Avoid Pedro Bay Corporation Lands | 2019-08-08 | 6.83 MB
116b | Alternatives 2 and 3 stream features | 2019-11-20 | 9 KB
39b | Amakdedori Port Wave Modeling – Data Sources and Input | 2019-12-12 | 4.89 MB
81 | Anchoring Plan for Lightering Locations | 2019-10-30 | 4.97 MB
147 | Appendix to Summarize Fish Habitat Modeling Procedures | 2020-05-31 | 8.03 MB
109h | Aquifer mapping used for the new groundwater model | 2019-10-30 | 79.7 MB
67 | Biological Assessments and Essential Fish Habitat Assessment | 2019-02-06 | 107.2 MB
157 | Bridge Construction Techniques | 2020-01-31 | 228 KB
130 | Bulk TSF Closure Design and Post-Closure Stability | 2020-01-31 | 107 KB
165 | Caisson Dock Lengthwise Cross-Section | 2020-04-30 | 657 KB
109o | Capture zone analysis and open pit WMP | 2019-11-20 | 51.39 MB
62a | Clarification of Cyanide Use in Expanded Mine Scenario | 2019-06-05 | 96 KB
167 | Clarification of Fish Habitat Modeling | 2020-05-08 | 209 KB
146 | Communication antenna specifications at Amakdedori Port | 2020-01-17 | 33 KB
56 | Compensatory Mitigation Plan | 2020-06-08 | 4.24 MB
109g | Comprehensive Water Modeling System | 2019-10-30 | 2.95 MB
66b | Concentrate Pipeline and Water Management | 2020-07-23 | 1.01 MB
9c | Concentrate Transfer to Bulk Carriers | 2019-07-26 | 14 KB
125 | Consistency with State Plans and Laws | 2019-07-26 | 26 KB
162 | Construction Schedule and Site Access During Construction | 2020-03-05 | 140 KB
BSEE 3 | Cook Inlet Natural Gas Pipeline: Archaeology Discoveries | 2019-12-30 | 13 KB
BSEE 1 | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2019-12-30 | 764 KB
BSEE1 | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2020-03-05 | 763 KB
BSEE1a | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2020-04-30 | 18 KB
BSEE2 | Cook Inlet Natural Gas Pipeline: Maintenance Schedule | 2020-03-05 | 589 KB
BSEE 2 | Cook Inlet Natural Gas Pipeline: Maintenance Schedule | 2019-12-30 | 589 KB
70 | Cost Information for Alternatives Screening | 2018-12-26 | 16 KB
97 | Cultural and Subsistence Figures Request | 2018-12-17 | 19.09 MB
113 | Cultural Data Refinement | 2019-10-30 | 10.94 MB
97b | Cultural Features in Analysis Area | 2019-02-06 | 241 KB
117 | Cultural Resource Surveys | 2019-06-05 | 121 KB
25 | Cultural Resources Survey Data | 2020-06-08 | 5.02 MB
25PDFONLY | Cultural Resources Survey Data | 2020-06-08 | 25 KB
25b | Cultural Resources Survey Data Followup | 2019-10-30 | 8.96 MB
97a | Cultural Resources Surveys for High/Low Potential | 2019-02-06 | 90 KB
82a | Dewatering Impacts to Wetland and Other Waters | 2019-10-30 | 176.83 MB
99 | Diamond Point Port Terminal Location | 2018-12-13 | 1.33 MB
76 | Dry Stack Bulk Tailings Information | 2018-12-26 | 15 KB
128 | East Kokhanok Ferry Terminal Land Availability | 2019-10-30 | 281 KB
16 | Ecological Zone Descriptions and GIS Layers | 2019-10-30 | 183.19 MB
119 | Eligibility Determinations Effort | 2019-06-05 | 154 KB
119a | Eligibility Determinations Execution and Mitigation Proposals | 2019-10-30 | 10 KB
8e | Embankment and Impoundment Summary Table | 2019-10-30 | 646 KB
159 | Estimate of Truck Traffic to Backhaul Container Wash Water to Mine Site | 2020-01-31 | 10 KB
109n | Expanded development scenario pit groundwater simulation | 2019-10-30 | 25.21 MB
109l | Fault sensitivity analysis – Bulk TSF west wall | 2019-10-30 | 276.41 MB
158 | Feedback on Permitting for Discharge of Process Water at Port Sites | 2020-01-31 | 9 KB
56a | Final Compensatory Mitigation Plan | 2020-01-31 | 17.42 MB
151 | Fish Density Estimates | 2019-11-13 | 190 KB
149 | Fish Habitat Modeling Results for Adult Resident Salmonids by Stream Reach | 2020-02-27 | 830 KB
140 | Fluvial Geomorphology Sampling Locations | 2019-09-20 | 149 KB
11a | Follow up on HDD Operations | 2020-01-31 | 17 KB
21i | Follow up on RFI 021e Addendum – Water Treatment Process Update | 2020-03-17 | 131 KB
21k | Follow up on RFI 021i – Water Treatment Process Update | 2020-04-30 | 69 KB
23b | Follow-up on Pit Wall Stability | 2019-10-30 | 61.42 MB
19b | Follow-up on Streamflow Reductions at End of Mine Life Excluding Water Treatment Plant Discharges (RFI 019 Part 2 Response) | 2020-06-08 | 2.66 MB
75a | Follow-up Questions on Downstream Dam for the Bulk TSF | 2019-10-30 | 4.76 MB
19a | Follow-up Questions on RFI 019 - Water Management Plan | 2019-10-30 | 2.26 MB
10a | Follow-up Questions on Tailings Characteristics | 2019-10-30 | 638 KB
21c | Follow-up Questions on Water Quality Predictions at Mine Site | 2019-10-30 | 2.86 MB
32b | Follow-up request on 32a for GIS polygon data for Proposed Project layout and access route. | 2019-10-30 | 998 KB
19c | Follow-up Requests on RFI 019 - Groundwater Modeling Report | 2019-10-30 | 10.43 MB
21d | Follow-up to 021 Water Quality-WTP processes and salt mass management | 2019-10-30 | 221 KB
9b | Follow-up to Dispersion Modeling - Copper in Dust Deposition | 2019-10-30 | 1.01 MB
8d | Follow-up to response to RFI 008b (Embankment Stability Analysis) | 2019-10-30 | 285 KB
8f | Follow-up to RFI 008f - Embankment and Impound Summary Table - Cross-Sections | 2019-10-30 | 833 KB
9a | Follow-up to RFI 009 Response: Dispersion and Deposition Modeling | 2019-10-30 | 2.01 MB
64a | Follow-up to RFI 064 response - Water Quality Criteria | 2019-10-30 | 447 KB
66a | Follow-up to RFI 066 Concentrate Pipeline Concept Description | 2019-10-30 | 1.4 MB
82b | Followup - Dewatering Impacts to Wetland and Other Waters | 2019-11-20 | 85.46 MB
7b | Followup on Air Quality Emission Inventories | 2020-01-31 | 786 KB
6b | Followup on Seepage Analysis | 2019-06-18 | 498 KB
6c | Followup on Seepage Analysis | 2020-01-31 | 1.62 MB
8g | Followup on Seismic Stability Analysis | 2020-01-31 | 14.55 MB
8h | Followup on Seismic Stability Analysis | 2020-01-31 | 325 KB
15a | Followup Question on RFI 015 Response - TSF Quarries | 2020-01-31 | 30 KB
6a | Followup Questions on Seepage Analysis | 2020-01-31 | 613 KB
65a | Followup Questions on Summer Only Ferry Operations | 2019-10-30 | 89 KB
108a | Followup to Main WMP Embankment Fill Volume | 2019-02-06 | 476 KB
14b | Followup to Mine Site Geotechnical Data | 2020-01-31 | 416.35 MB
109e | Followup to new groundwater model | 2020-01-31 | 16.15 MB
108b | Followup to RFIs 108/108a - Main WMP Embankment Fill Volume | 2019-02-06 | 102 KB
134 | Fugitive Dust Control Plan | 2020-01-31 | 187 KB
21f | Geochemical Evaluation | 2019-09-20 | 415 KB
105 | Geochemical Testing Update | 2019-01-04 | 259 KB
14a | Geotechnical Boring Program Report | 2019-10-30 | 55 KB
148 | GIS shape files for Biological Assessment Action Area | 2019-10-30 | 654 KB
132 | Groundwater Drawdown Zone GIS Data | 2019-10-30 | 149.57 MB
109d | Groundwater model validation and sensitivity analysis | 2019-10-30 | 378.41 MB
109b | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-10-30 | 1.53 MB
109a | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-02-11 | 5.94 MB
109c | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-02-06 | 1.54 MB
109 | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-10-30 | 5.96 MB
31 | HDDs Under Rivers | 2019-10-30 | 19 KB
109j | Hydraulic conductivity data used for the new groundwater model | 2019-09-20 | 11.53 MB
90 | In Pit Crushing and Conveying | 2019-10-30 | 4.49 MB
82c | Indirect Impacts of Dewatering to Wetlands and Other Waters under Mine Expansion | 2020-04-30 | 31.42 MB
114 | Inquiry for Cultural Resources on Native Allotments | 2019-02-22 | 88 KB
144 | Intragravel Spawning Temperature Data | 2019-10-30 | 9 KB
133 | Invasive Species Management Plan | 2020-01-31 | 2.19 MB
139 | Lake Clark Fault Information | 2020-01-31 | 16.77 MB
129 | Low Permeability Material Quantities | 2020-01-31 | 194 KB
101 | Main Water Management Pond Design Change | 2018-12-17 | 805 KB
108 | Main WMP Embankment Fill Volume | 2019-02-06 | 74 KB
106a | Mass Loading Figures Update | 2020-04-30 | 39 KB
35 | Material Sites Details and Blasting Information | 2020-01-31 | 25 KB
39a | Metocean Measurement Program Data | 2019-08-08 | 915 KB
14 | Mine Site Geotechnical Data: GIS Layers and TSF Coverage | 2019-01-18 | 901 KB
58 | Mine Site Safety Control Area | 2020-01-31 | 1.72 MB
47 | Mine-related changes in water temperatures in project area tributaries | 2019-10-30 | 16.55 MB
71b | Mitigation for Analysis in the EIS | 2019-10-30 | 976 KB
135 | Monitoring and Adaptive Management Plan | 2020-01-31 | 7.87 MB
73 | No Action Alternative | 2018-12-12 | 302 KB
80 | North Access Natural Gas Pipeline Route | 2019-10-30 | 8.32 MB
155 | North Fork and South Fork Koktuli Rivers Baseline Habitat Data | 2019-11-20 | 11 KB
110 | NP/AP Ratio | 2019-02-06 | 3.6 MB
126 | Operational Measures for Spill Prevention | 2019-10-30 | 147 KB
164 | Permanent Berm in Iliamna Lake for Natural Gas Pipeline | 2020-04-30 | 10 KB
131 | Permitting for Large Mine Projects in Alaska | 2019-10-30 | 14 KB
109m | Pit lake hydraulic containment | 2019-10-30 | 43.56 MB
109p | Pit lake hydraulic containment follow-up | 2019-12-11 | 27.32 MB
109k | Potential Headwaters Streams dewatering | 2019-10-30 | 56.32 MB
27 | Project Logistics and Employment for Socioeconomics and Transportation | 2020-01-31 | 24 KB
143a | Project Optimizations | 2020-07-23 | 31 KB
143 | Project Optimizations | 2019-10-30 | 152 KB
109i | Prucha 2019 – Comments Potentially Applicable to New Groundwater Model (BGC 2019) | 2019-10-30 | 873 KB
8i | Pseudo-static Stability Analyses - Other Embankments | 2019-10-30 | 26 KB
102 | Pyramid Deposit Location Alternative | 2018-12-12 | 99 KB
115 | Reclamation and Closure Plan | 2019-10-30 | 93.88 MB
123 | Restoration Plan for temporary impacts from construction | 2019-06-18 | 2.68 MB
156 | Review of Cultural Resources Documents | 2020-01-31 | 12 KB
10 | RFI 10: Tailings Characteristics | 2018-08-02 | 50.06 MB
11 | RFI 11: Pipeline HDD and Bluff Erosion | 2018-05-22 | 36 KB
13 | RFI 13: Iliamna Lake and Pipeline Landfall Hazards | 2018-09-27 | 13.29 MB
152 | RFI 152: Update to Table K2-5 Mine Site Supplies and Quantities | 2020-01-31 | 22 KB
15 | RFI 15: TSF Quarries | 2018-07-30 | 56 KB
15b | RFI 15b: Followup Question on RFI 015 Response - TSF Quarries | 2018-08-02 | 3.2 MB
17 | RFI 17: SEBD Chapter for Trace Elements (Bristol Bay) | 2018-05-22 | 16 KB
18 | RFI 18: LGO stockpile Liner | 2018-05-22 | 21 KB
19d | RFI 19d: Pit Lake Rise | 2018-10-05 | 44 KB
1 | RFI 1: Data Needs and Proposed Timelines for Information | 2018-08-02 | 157 KB
20 | RFI 20: Water Treatment | 2018-05-30 | 235 KB
21 | RFI 21: Water Quality Predictions at Mine Site | 2018-10-05 | 17 KB
21a | RFI 21a: Follow up Request on RFI 021 - Water Quality Predictions at Mine Site | 2018-10-05 | 1.61 MB
21b | RFI 21b: Follow up Request on RFI 021 - Water Quality Modeling | 2018-10-05 | 20 KB
22 | RFI 22: Water Withdrawals, Roads and Pipeline | 2018-05-22 | 20 KB
22a | RFI 22a: Water Extraction and Supply at Port Facilities | 2018-08-02 | 19 KB
22b | RFI 22b: Followup Request for RFI 022 Regarding Hydrostatic Test Water | 2018-08-09 | 20 KB
23 | RFI 23: Pit Wall Stability | 2018-10-05 | 761 KB
24 | RFI 24: Plans for Reclamation and Restoration | 2018-05-22 | 37 KB
26 | RFI 26: Detailed Land Status | 2018-05-30 | 16 KB
27a | RFI 27a: Followup Questions on RFI 027 - Aircraft and Noise | 2018-08-02 | 23 KB
27b | RFI 27b: Additional Transportation Information | 2018-10-05 | 17.31 MB
28 | RFI 28: TSF IDF and Freeboard | 2018-10-05 | 12.31 MB
28a | RFI 28a: Follow-up Questions on RFI 028 - IDF, Freeboard, Precipitation Inputs, and Spillways | 2018-10-05 | 5.05 MB
28b | RFI 28b: Follow-up Questions on RFI 028a - Climate Change Inputs to IDF/Freeboard | 2018-10-05 | 10.35 MB
29 | RFI 29: Ferry Propeller Design Specifications | 2018-05-22 | 22 KB
2 | RFI 2: Grouped Vegetation Type GIS Data | 2018-05-30 | 30.33 MB
30 | RFI 30: Marine Mammal Impacts Analysis - Acoustic Information | 2018-08-09 | 18.5 MB
32 | RFI 32: Conceptual Design and Feasibility Information for Options in March 20, 2018 Technical Note | 2018-08-09 | 16.7 MB
23a | RFI 32a: Follow-up Questions on RFI 023 Pit Wall Stability | 2018-10-05 | 953 KB
32a | RFI 32a: Followup Requests on RFI 032 - Conceptual Design and Feasibility Information for Options in March 20, 2018 Technical Note | 2018-08-09 | 3.4 MB
33 | RFI 33: Project Option for Shallower Port Dredging Depth | 2018-08-09 | 23 KB
34a | RFI 34a: Visual Resource Data | 2018-10-05 | 25.98 MB
34b | RFI 34b: Visual Resource Data | 2018-10-19 | 3.19 MB
34c | RFI 34c: Viewshed for Alternatives | 2018-10-19 | 5.13 MB
36 | RFI 36: Waterbody substrate and turbidity | 2018-09-07 | 78 KB
37 | RFI 37: Construction Schedule and Site Access During Construction | 2018-08-02 | 126 KB
38 | RFI 38: Noise: Mine Site Equipment/Vehicle Roster | 2018-09-07 | 99 KB
39 | RFI 39: Amakdedori - Oceanographic Data | 2018-09-07 | 3.97 MB
3 | RFI 3: ADF&G Subsistence GIS Data from Technical Papers | 2018-08-09 | 4.41 MB
40 | RFI 40: Mine Site Water GIS Data | 2018-08-02 | 177 KB
42 | RFI 42: History of Exploration in Alaska | 2018-09-27 | 1.29 MB
43 | RFI 43: Diesel Tanks at Mine Site | 2018-08-02 | 37 KB
44 | RFI 44: Cultural Resources Place Name Data | 2018-08-09 | 17 KB
45 | RFI 45: Concentrate Containers - Spill and Integrity Data | 2018-08-16 | 654 KB
46 | RFI 46: 2010 Fish Habitat Modeling | 2018-08-09 | 16 KB
48 | RFI 48: Revised Habitat Time Series Analysis | 2018-10-19 | 3.37 MB
49 | RFI 49: Water Quality Reference Document | 2018-08-02 | 15.03 MB
4 | RFI 4: SEBD 07 SW Hydrology OCT15 - Missing Appendix 7A-E Figures and Tables | 2018-05-30 | 14.31 MB
50 | RFI 50: GIS Data for Chapter 10 EBD Trace Elements - Shallow Soil Sample Locations | 2018-08-09 | 50 KB
51 | RFI 51: HDD Water Handling | 2018-08-16 | 23 KB
52 | RFI 52: Incident Risk Assessment for Ice Breaking Ferrry | 2018-08-16 | 943 KB
53 | RFI 53: Water Chemistry Field Measurements | 2018-08-09 | 17 KB
54 | RFI 54: Dry Stack Tailings | 2018-10-05 | 830 KB
55 | RFI 55: PAG-Pyritic Tailings Storage Facility, Construction and Closure | 2018-10-05 | 885 KB
55a | RFI 55a: Follow-up to response to RFI 055 PAG/Pyritic TSF | 2018-10-05 | 127 KB
57 | RFI 57: Drinking Water Data | 2018-08-09 | 50 KB
59 | RFI 59: Project Optimization Study Cited with Regard to Throughput in PLP Technical Note on Project Options and Screening Criteria | 2018-09-27 | 27.07 MB
5 | RFI 5: Stability of Port Structures | 2018-08-02 | 4.76 MB
60 | RFI 60: Diesel Hauling by truck, Ferry and Marine Vessel - Transport and Spill Data | 2018-08-16 | 394 KB
61 | RFI 61: Wildlife Resources References | 2018-08-09 | 5.76 MB
63 | RFI 63: Diamond Point Port Water Depth and Pipeline Alignment | 2018-09-27 | 54 KB
64 | RFI 64: Regulation of Effluent Discharges | 2018-09-07 | 290 KB
66 | RFI 66: Concentrate Pipeline Concept Description | 2018-10-18 | 3.59 MB
68 | RFI 68: Water and Sediment Quality Data Tales from EBD/SEBDs | 2018-10-05 | 8.8 MB
68a | RFI 68a: Additional Water Quality Tables | 2018-10-05 | 443 KB
68b | RFI 68b: Additional Water Quality Tables | 2018-10-05 | 168 KB
69 | RFI 69: Tailings Disposal Options | 2018-10-05 | 6.76 MB
71 | RFI 71: Mitigation for Analysis in EIS | 2018-09-28 | 33 KB
71a | RFI 71a: Followup on RFI 071 Response - Mitigation for Analysis in the EIS | 2018-10-05 | 42 KB
72 | RFI 72: Pile Supported Dock Concept Description | 2018-10-05 | 2.98 MB
74 | RFI 74: Ferry Terminal Site East of North Shore Site | 2018-10-05 | 36 KB
75 | RFI 75: Downstream Dam for the Bulk TSF | 2018-10-05 | 301 KB
78 | RFI 78: Kokhanok East Ferry Terminal Site | 2018-10-05 | 4.23 MB
79 | RFI 79: North Shore East Ferry Terminal Site | 2018-10-05 | 1.18 MB
83 | RFI 83: GIS Data for Action Alternatives - Biological Resources | 2018-10-19 | 14.96 MB
84 | RFI 84: Transportation Corridor Construction/Blasting | 2018-10-19 | 8.52 MB
86 | RFI 86: Fish/Waterbody Crossings | 2018-10-19 | 38 KB
8 | RFI 8: Embankment Static and Seismic Stability | 2018-09-07 | 6.51 MB
8a | RFI 8a: Followup on Embankment Stability | 2018-10-05 | 8.21 MB
8b | RFI 8b: Followup on 008/008a Embankment Stability Analyses | 2018-10-05 | 276 KB
8c | RFI 8c: Followup on 008a - Seismic Analyses | 2018-10-05 | 39 KB
91 | RFI 91: Bulk TSF Cover Options | 2018-10-19 | 215 KB
92 | RFI 92: Tailings Treatment Options | 2018-10-19 | 207 KB
93 | RFI 93: Dimensions of proposed project and area of proposed impacts to Navigable WOUS | 2018-10-19 | 8.91 MB
62 | Scenario for Expanded Development of Pebble | 2020-01-31 | 9.68 MB
6 | Seepage Analysis | 2020-01-31 | 238 KB
160 | Seismic Design Considerations, Caisson Dock | 2020-01-17 | 5.53 MB
150 | Siting Criteria for Main Water Management Pond | 2020-05-31 | 2.03 MB
8j | Static Stability Analysis, Main WMP | 2019-10-30 | 48 KB
109f | Streamflow estimates from new groundwater model | 2020-01-09 | 149.78 MB
97c | Subsistence Figures Update Request | 2020-02-06 | 5.8 MB
65 | Summer Only Ferry Operations | 2020-05-31 | 4.27 MB
89 | Supplement Wildlife Harvest and Subsistence Fishing Harvest Data | 2018-12-13 | 288 KB
118 | Surface Water Hydrology Data | 2019-10-30 | 8.8 MB
109q | Surface Water Model Follow-up | 2019-12-11 | 36 KB
87 | Surface water runoff and treated water management and outfalls: Ferry Terminals and Amakdedori Port | 2019-10-30 | 72 KB
88 | Traditional routes and trails | 2018-10-19 | 2.18 MB
95 | Trumpeter Swan Distribution Data | 2019-01-04 | 2.86 MB
98 | TSF Options, Mine Area | 2018-12-17 | 10.17 MB
112 | Tsunami Design for Port Facilities | 2020-01-31 | 193 KB
84a | Update Construction and Blasting Footprint | 2019-11-13 | 7.56 MB
71c | Update of Avoidance and Minimization Measures in EIS | 2020-05-08 | 261 KB
112a | Update of Tsunami Design | 2020-01-31 | 11 KB
113b | Updated Cultural Resources Data | 2020-07-23 | 1.16 MB
97d | Updated Subsistence Figures | 2020-07-23 | 6.02 MB
34g | Updated Viewshed and Simulation | 2020-07-23 | 5.63 MB
34e | Updated Viewshed Figures | 2020-01-31 | 21.4 MB
100 | Upgrades to Newhalen River Road for Alternatives 2 and 3 | 2018-12-12 | 99 KB
163 | Vessel Route for Bulk Carriers | 2020-05-01 | 3.39 MB
34f | Visual Resource Data | 2019-12-11 | 16.02 MB
34d | Visual Resources Clarification | 2019-10-30 | 15.68 MB
87a | Water and Sewage Treatment Followup | 2019-07-26 | 107 KB
19 | Water Balance, Groundwater Model, and Streamflow Reduction | 2019-10-30 | 41.65 MB
21g | Water Quality Model Update and Sensitivity/Uncertainty Analyses | 2020-01-08 | 52.38 MB
111 | Water Quality Statistics | 2019-02-06 | 121 KB
21j | Water Treatment for Mercury | 2020-04-30 | 88 KB
21h | Water Treatment Process Information – Follow-up to RFI 021e | 2020-04-30 | 93 KB
21e | Water Treatment Process Update | 2020-01-31 | 3.37 MB
77 | Water Withdrawals for Select Alternative Options | 2019-10-30 | 2.47 MB
153 | Waterbody Crossings | 2019-11-13 | 40.13 MB
161 | Watershed Model and Streamflow Change | 2020-02-27 | 4.88 MB
104 | Watershed Model Documentation | 2019-01-11 | 5.8 MB
138 | Watershed model water balance | 2019-10-30 | 92 KB
116 | Wetlands 2019 Field Verified Data | 2019-10-30 | 579.82 MB
116c | Wetlands and Vegetation Data Mapping for Alternative 3 | 2020-07-23 | 9 KB
116a | Wetlands Mapping Data | 2019-11-20 | 1.15 GB
82 | Wetlands Temporary and Indirect Impacts | 2020-01-31 | 186.06 MB
96 | Wildlife Distribution Data | 2019-01-18 | 90 KB
122 | Wildlife Management | 2019-06-18 | 286 KB
145 | WTP Discharge Temperature | 2019-12-11 | 1.49 MB
166 | WTP Schematics Update | 2020-05-08 | 119 KB
Title

## By RFI number
Number | Title | Upload Date | Size
1 | RFI 1: Data Needs and Proposed Timelines for Information | 2018-08-02 | 157 KB
2 | RFI 2: Grouped Vegetation Type GIS Data | 2018-05-30 | 30.33 MB
3 | RFI 3: ADF&G Subsistence GIS Data from Technical Papers | 2018-08-09 | 4.41 MB
4 | RFI 4: SEBD 07 SW Hydrology OCT15 - Missing Appendix 7A-E Figures and Tables | 2018-05-30 | 14.31 MB
5 | RFI 5: Stability of Port Structures | 2018-08-02 | 4.76 MB
6 | Seepage Analysis | 2020-01-31 | 238 KB
7 | Air Quality Emission Inventories | 2020-01-31 | 3.73 MB
8 | RFI 8: Embankment Static and Seismic Stability | 2018-09-07 | 6.51 MB
9 | Air Quality Dispersion Modeling | 2020-01-31 | 3.31 MB
10 | RFI 10: Tailings Characteristics | 2018-08-02 | 50.06 MB
11 | RFI 11: Pipeline HDD and Bluff Erosion | 2018-05-22 | 36 KB
12 | Air Quality Related Values | 2018-12-12 | 125 KB
13 | RFI 13: Iliamna Lake and Pipeline Landfall Hazards | 2018-09-27 | 13.29 MB
14 | Mine Site Geotechnical Data: GIS Layers and TSF Coverage | 2019-01-18 | 901 KB
15 | RFI 15: TSF Quarries | 2018-07-30 | 56 KB
16 | Ecological Zone Descriptions and GIS Layers | 2019-10-30 | 183.19 MB
17 | RFI 17: SEBD Chapter for Trace Elements (Bristol Bay) | 2018-05-22 | 16 KB
18 | RFI 18: LGO stockpile Liner | 2018-05-22 | 21 KB
19 | Water Balance, Groundwater Model, and Streamflow Reduction | 2019-10-30 | 41.65 MB
20 | RFI 20: Water Treatment | 2018-05-30 | 235 KB
21 | RFI 21: Water Quality Predictions at Mine Site | 2018-10-05 | 17 KB
22 | RFI 22: Water Withdrawals, Roads and Pipeline | 2018-05-22 | 20 KB
23 | RFI 23: Pit Wall Stability | 2018-10-05 | 761 KB
24 | RFI 24: Plans for Reclamation and Restoration | 2018-05-22 | 37 KB
25 | Cultural Resources Survey Data | 2020-06-08 | 5.02 MB
26 | RFI 26: Detailed Land Status | 2018-05-30 | 16 KB
27 | Project Logistics and Employment for Socioeconomics and Transportation | 2020-01-31 | 24 KB
28 | RFI 28: TSF IDF and Freeboard | 2018-10-05 | 12.31 MB
29 | RFI 29: Ferry Propeller Design Specifications | 2018-05-22 | 22 KB
30 | RFI 30: Marine Mammal Impacts Analysis - Acoustic Information | 2018-08-09 | 18.5 MB
31 | HDDs Under Rivers | 2019-10-30 | 19 KB
32 | RFI 32: Conceptual Design and Feasibility Information for Options in March 20, 2018 Technical Note | 2018-08-09 | 16.7 MB
33 | RFI 33: Project Option for Shallower Port Dredging Depth | 2018-08-09 | 23 KB
35 | Material Sites Details and Blasting Information | 2020-01-31 | 25 KB
36 | RFI 36: Waterbody substrate and turbidity | 2018-09-07 | 78 KB
37 | RFI 37: Construction Schedule and Site Access During Construction | 2018-08-02 | 126 KB
38 | RFI 38: Noise: Mine Site Equipment/Vehicle Roster | 2018-09-07 | 99 KB
39 | RFI 39: Amakdedori - Oceanographic Data | 2018-09-07 | 3.97 MB
40 | RFI 40: Mine Site Water GIS Data | 2018-08-02 | 177 KB
41 | Airport Air Traffic Data | 2020-02-27 | 9 KB
42 | RFI 42: History of Exploration in Alaska | 2018-09-27 | 1.29 MB
43 | RFI 43: Diesel Tanks at Mine Site | 2018-08-02 | 37 KB
44 | RFI 44: Cultural Resources Place Name Data | 2018-08-09 | 17 KB
45 | RFI 45: Concentrate Containers - Spill and Integrity Data | 2018-08-16 | 654 KB
46 | RFI 46: 2010 Fish Habitat Modeling | 2018-08-09 | 16 KB
47 | Mine-related changes in water temperatures in project area tributaries | 2019-10-30 | 16.55 MB
48 | RFI 48: Revised Habitat Time Series Analysis | 2018-10-19 | 3.37 MB
49 | RFI 49: Water Quality Reference Document | 2018-08-02 | 15.03 MB
50 | RFI 50: GIS Data for Chapter 10 EBD Trace Elements - Shallow Soil Sample Locations | 2018-08-09 | 50 KB
51 | RFI 51: HDD Water Handling | 2018-08-16 | 23 KB
52 | RFI 52: Incident Risk Assessment for Ice Breaking Ferrry | 2018-08-16 | 943 KB
53 | RFI 53: Water Chemistry Field Measurements | 2018-08-09 | 17 KB
54 | RFI 54: Dry Stack Tailings | 2018-10-05 | 830 KB
55 | RFI 55: PAG-Pyritic Tailings Storage Facility, Construction and Closure | 2018-10-05 | 885 KB
56 | Compensatory Mitigation Plan | 2020-06-08 | 4.24 MB
57 | RFI 57: Drinking Water Data | 2018-08-09 | 50 KB
58 | Mine Site Safety Control Area | 2020-01-31 | 1.72 MB
59 | RFI 59: Project Optimization Study Cited with Regard to Throughput in PLP Technical Note on Project Options and Screening Criteria | 2018-09-27 | 27.07 MB
60 | RFI 60: Diesel Hauling by truck, Ferry and Marine Vessel - Transport and Spill Data | 2018-08-16 | 394 KB
61 | RFI 61: Wildlife Resources References | 2018-08-09 | 5.76 MB
62 | Scenario for Expanded Development of Pebble | 2020-01-31 | 9.68 MB
63 | RFI 63: Diamond Point Port Water Depth and Pipeline Alignment | 2018-09-27 | 54 KB
64 | RFI 64: Regulation of Effluent Discharges | 2018-09-07 | 290 KB
65 | Summer Only Ferry Operations | 2020-05-31 | 4.27 MB
66 | RFI 66: Concentrate Pipeline Concept Description | 2018-10-18 | 3.59 MB
67 | Biological Assessments and Essential Fish Habitat Assessment | 2019-02-06 | 107.2 MB
68 | RFI 68: Water and Sediment Quality Data Tales from EBD/SEBDs | 2018-10-05 | 8.8 MB
69 | RFI 69: Tailings Disposal Options | 2018-10-05 | 6.76 MB
70 | Cost Information for Alternatives Screening | 2018-12-26 | 16 KB
71 | RFI 71: Mitigation for Analysis in EIS | 2018-09-28 | 33 KB
72 | RFI 72: Pile Supported Dock Concept Description | 2018-10-05 | 2.98 MB
73 | No Action Alternative | 2018-12-12 | 302 KB
74 | RFI 74: Ferry Terminal Site East of North Shore Site | 2018-10-05 | 36 KB
75 | RFI 75: Downstream Dam for the Bulk TSF | 2018-10-05 | 301 KB
76 | Dry Stack Bulk Tailings Information | 2018-12-26 | 15 KB
77 | Water Withdrawals for Select Alternative Options | 2019-10-30 | 2.47 MB
78 | RFI 78: Kokhanok East Ferry Terminal Site | 2018-10-05 | 4.23 MB
79 | RFI 79: North Shore East Ferry Terminal Site | 2018-10-05 | 1.18 MB
80 | North Access Natural Gas Pipeline Route | 2019-10-30 | 8.32 MB
81 | Anchoring Plan for Lightering Locations | 2019-10-30 | 4.97 MB
82 | Wetlands Temporary and Indirect Impacts | 2020-01-31 | 186.06 MB
83 | RFI 83: GIS Data for Action Alternatives - Biological Resources | 2018-10-19 | 14.96 MB
84 | RFI 84: Transportation Corridor Construction/Blasting | 2018-10-19 | 8.52 MB
85 | 2018 Field Data/Biological Resources | 2019-10-30 | 5.79 MB
86 | RFI 86: Fish/Waterbody Crossings | 2018-10-19 | 38 KB
87 | Surface water runoff and treated water management and outfalls: Ferry Terminals and Amakdedori Port | 2019-10-30 | 72 KB
88 | Traditional routes and trails | 2018-10-19 | 2.18 MB
89 | Supplement Wildlife Harvest and Subsistence Fishing Harvest Data | 2018-12-13 | 288 KB
90 | In Pit Crushing and Conveying | 2019-10-30 | 4.49 MB
91 | RFI 91: Bulk TSF Cover Options | 2018-10-19 | 215 KB
92 | RFI 92: Tailings Treatment Options | 2018-10-19 | 207 KB
93 | RFI 93: Dimensions of proposed project and area of proposed impacts to Navigable WOUS | 2018-10-19 | 8.91 MB
94 | Alternative Option to Develop Pebble East Using Underground Mining | 2019-10-30 | 3.2 MB
95 | Trumpeter Swan Distribution Data | 2019-01-04 | 2.86 MB
96 | Wildlife Distribution Data | 2019-01-18 | 90 KB
97 | Cultural and Subsistence Figures Request | 2018-12-17 | 19.09 MB
98 | TSF Options, Mine Area | 2018-12-17 | 10.17 MB
99 | Diamond Point Port Terminal Location | 2018-12-13 | 1.33 MB
100 | Upgrades to Newhalen River Road for Alternatives 2 and 3 | 2018-12-12 | 99 KB
101 | Main Water Management Pond Design Change | 2018-12-17 | 805 KB
102 | Pyramid Deposit Location Alternative | 2018-12-12 | 99 KB
104 | Watershed Model Documentation | 2019-01-11 | 5.8 MB
105 | Geochemical Testing Update | 2019-01-04 | 259 KB
106 | Additional Water Quality Data | 2019-02-11 | 3.62 MB
107 | Access Roads to Water Extraction Sites | 2019-01-11 | 95 KB
108 | Main WMP Embankment Fill Volume | 2019-02-06 | 74 KB
109 | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-10-30 | 5.96 MB
110 | NP/AP Ratio | 2019-02-06 | 3.6 MB
111 | Water Quality Statistics | 2019-02-06 | 121 KB
112 | Tsunami Design for Port Facilities | 2020-01-31 | 193 KB
113 | Cultural Data Refinement | 2019-10-30 | 10.94 MB
114 | Inquiry for Cultural Resources on Native Allotments | 2019-02-22 | 88 KB
115 | Reclamation and Closure Plan | 2019-10-30 | 93.88 MB
116 | Wetlands 2019 Field Verified Data | 2019-10-30 | 579.82 MB
117 | Cultural Resource Surveys | 2019-06-05 | 121 KB
118 | Surface Water Hydrology Data | 2019-10-30 | 8.8 MB
119 | Eligibility Determinations Effort | 2019-06-05 | 154 KB
120 | Alternative Alignment for Natural Gas Pipeline | 2019-10-30 | 3.07 MB
121 | Alternative ferry route and natural gas pipeline crossing alignment across Iliamna Lake | 2019-06-18 | 13.2 MB
122 | Wildlife Management | 2019-06-18 | 286 KB
123 | Restoration Plan for temporary impacts from construction | 2019-06-18 | 2.68 MB
124 | Additional Project Simulation | 2019-07-26 | 634 KB
125 | Consistency with State Plans and Laws | 2019-07-26 | 26 KB
126 | Operational Measures for Spill Prevention | 2019-10-30 | 147 KB
127 | Alternative Road Alignment to Avoid Pedro Bay Corporation Lands | 2019-08-08 | 6.83 MB
128 | East Kokhanok Ferry Terminal Land Availability | 2019-10-30 | 281 KB
129 | Low Permeability Material Quantities | 2020-01-31 | 194 KB
130 | Bulk TSF Closure Design and Post-Closure Stability | 2020-01-31 | 107 KB
131 | Permitting for Large Mine Projects in Alaska | 2019-10-30 | 14 KB
132 | Groundwater Drawdown Zone GIS Data | 2019-10-30 | 149.57 MB
133 | Invasive Species Management Plan | 2020-01-31 | 2.19 MB
134 | Fugitive Dust Control Plan | 2020-01-31 | 187 KB
135 | Monitoring and Adaptive Management Plan | 2020-01-31 | 7.87 MB
136 | Alternative 1 Airport Spur Road Land Availability | 2019-09-20 | 273 KB
137 | Air Quality Dispersion Modeling | 2019-10-30 | 33.25 MB
138 | Watershed model water balance | 2019-10-30 | 92 KB
139 | Lake Clark Fault Information | 2020-01-31 | 16.77 MB
140 | Fluvial Geomorphology Sampling Locations | 2019-09-20 | 149 KB
141 | Air Quality Dispersion Modeling Deposition Input Details | 2019-10-30 | 2.85 MB
143 | Project Optimizations | 2019-10-30 | 152 KB
144 | Intragravel Spawning Temperature Data | 2019-10-30 | 9 KB
145 | WTP Discharge Temperature | 2019-12-11 | 1.49 MB
146 | Communication antenna specifications at Amakdedori Port | 2020-01-17 | 33 KB
147 | Appendix to Summarize Fish Habitat Modeling Procedures | 2020-05-31 | 8.03 MB
148 | GIS shape files for Biological Assessment Action Area | 2019-10-30 | 654 KB
149 | Fish Habitat Modeling Results for Adult Resident Salmonids by Stream Reach | 2020-02-27 | 830 KB
150 | Siting Criteria for Main Water Management Pond | 2020-05-31 | 2.03 MB
151 | Fish Density Estimates | 2019-11-13 | 190 KB
152 | RFI 152: Update to Table K2-5 Mine Site Supplies and Quantities | 2020-01-31 | 22 KB
153 | Waterbody Crossings | 2019-11-13 | 40.13 MB
154 | Alternate Newhalen River Crossing | 2020-01-31 | 839 KB
155 | North Fork and South Fork Koktuli Rivers Baseline Habitat Data | 2019-11-20 | 11 KB
156 | Review of Cultural Resources Documents | 2020-01-31 | 12 KB
157 | Bridge Construction Techniques | 2020-01-31 | 228 KB
158 | Feedback on Permitting for Discharge of Process Water at Port Sites | 2020-01-31 | 9 KB
159 | Estimate of Truck Traffic to Backhaul Container Wash Water to Mine Site | 2020-01-31 | 10 KB
160 | Seismic Design Considerations, Caisson Dock | 2020-01-17 | 5.53 MB
161 | Watershed Model and Streamflow Change | 2020-02-27 | 4.88 MB
162 | Construction Schedule and Site Access During Construction | 2020-03-05 | 140 KB
163 | Vessel Route for Bulk Carriers | 2020-05-01 | 3.39 MB
164 | Permanent Berm in Iliamna Lake for Natural Gas Pipeline | 2020-04-30 | 10 KB
165 | Caisson Dock Lengthwise Cross-Section | 2020-04-30 | 657 KB
166 | WTP Schematics Update | 2020-05-08 | 119 KB
167 | Clarification of Fish Habitat Modeling | 2020-05-08 | 209 KB
168 | Alternative 3 Base Case Optimizations | 2020-07-23 | 4.9 MB
106a | Mass Loading Figures Update | 2020-04-30 | 39 KB
108a | Followup to Main WMP Embankment Fill Volume | 2019-02-06 | 476 KB
108b | Followup to RFIs 108/108a - Main WMP Embankment Fill Volume | 2019-02-06 | 102 KB
109a | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-02-11 | 5.94 MB
109b | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-10-30 | 1.53 MB
109c | Groundwater Model, Followup to 12/11/18 Technical Meeting Action Items | 2019-02-06 | 1.54 MB
109d | Groundwater model validation and sensitivity analysis | 2019-10-30 | 378.41 MB
109e | Followup to new groundwater model | 2020-01-31 | 16.15 MB
109f | Streamflow estimates from new groundwater model | 2020-01-09 | 149.78 MB
109g | Comprehensive Water Modeling System | 2019-10-30 | 2.95 MB
109h | Aquifer mapping used for the new groundwater model | 2019-10-30 | 79.7 MB
109i | Prucha 2019 – Comments Potentially Applicable to New Groundwater Model (BGC 2019) | 2019-10-30 | 873 KB
109j | Hydraulic conductivity data used for the new groundwater model | 2019-09-20 | 11.53 MB
109k | Potential Headwaters Streams dewatering | 2019-10-30 | 56.32 MB
109l | Fault sensitivity analysis – Bulk TSF west wall | 2019-10-30 | 276.41 MB
109m | Pit lake hydraulic containment | 2019-10-30 | 43.56 MB
109n | Expanded development scenario pit groundwater simulation | 2019-10-30 | 25.21 MB
109o | Capture zone analysis and open pit WMP | 2019-11-20 | 51.39 MB
109p | Pit lake hydraulic containment follow-up | 2019-12-11 | 27.32 MB
109q | Surface Water Model Follow-up | 2019-12-11 | 36 KB
10a | Follow-up Questions on Tailings Characteristics | 2019-10-30 | 638 KB
112a | Update of Tsunami Design | 2020-01-31 | 11 KB
113a | Addendum to the Cultural Resources Summary Report | 2020-04-30 | 1.36 MB
113b | Updated Cultural Resources Data | 2020-07-23 | 1.16 MB
116a | Wetlands Mapping Data | 2019-11-20 | 1.15 GB
116b | Alternatives 2 and 3 stream features | 2019-11-20 | 9 KB
116c | Wetlands and Vegetation Data Mapping for Alternative 3 | 2020-07-23 | 9 KB
117a | 2019 Cultural Resource Surveys Clarification | 2020-01-31 | 2.58 MB
119a | Eligibility Determinations Execution and Mitigation Proposals | 2019-10-30 | 10 KB
11a | Follow up on HDD Operations | 2020-01-31 | 17 KB
143a | Project Optimizations | 2020-07-23 | 31 KB
14a | Geotechnical Boring Program Report | 2019-10-30 | 55 KB
14b | Followup to Mine Site Geotechnical Data | 2020-01-31 | 416.35 MB
15a | Followup Question on RFI 015 Response - TSF Quarries | 2020-01-31 | 30 KB
15b | RFI 15b: Followup Question on RFI 015 Response - TSF Quarries | 2018-08-02 | 3.2 MB
19a | Follow-up Questions on RFI 019 - Water Management Plan | 2019-10-30 | 2.26 MB
19b | Follow-up on Streamflow Reductions at End of Mine Life Excluding Water Treatment Plant Discharges (RFI 019 Part 2 Response) | 2020-06-08 | 2.66 MB
19c | Follow-up Requests on RFI 019 - Groundwater Modeling Report | 2019-10-30 | 10.43 MB
19d | RFI 19d: Pit Lake Rise | 2018-10-05 | 44 KB
21a | RFI 21a: Follow up Request on RFI 021 - Water Quality Predictions at Mine Site | 2018-10-05 | 1.61 MB
21b | RFI 21b: Follow up Request on RFI 021 - Water Quality Modeling | 2018-10-05 | 20 KB
21c | Follow-up Questions on Water Quality Predictions at Mine Site | 2019-10-30 | 2.86 MB
21d | Follow-up to 021 Water Quality-WTP processes and salt mass management | 2019-10-30 | 221 KB
21e | Water Treatment Process Update | 2020-01-31 | 3.37 MB
21f | Geochemical Evaluation | 2019-09-20 | 415 KB
21g | Water Quality Model Update and Sensitivity/Uncertainty Analyses | 2020-01-08 | 52.38 MB
21h | Water Treatment Process Information – Follow-up to RFI 021e | 2020-04-30 | 93 KB
21i | Follow up on RFI 021e Addendum – Water Treatment Process Update | 2020-03-17 | 131 KB
21j | Water Treatment for Mercury | 2020-04-30 | 88 KB
21k | Follow up on RFI 021i – Water Treatment Process Update | 2020-04-30 | 69 KB
22a | RFI 22a: Water Extraction and Supply at Port Facilities | 2018-08-02 | 19 KB
22b | RFI 22b: Followup Request for RFI 022 Regarding Hydrostatic Test Water | 2018-08-09 | 20 KB
23a | RFI 32a: Follow-up Questions on RFI 023 Pit Wall Stability | 2018-10-05 | 953 KB
23b | Follow-up on Pit Wall Stability | 2019-10-30 | 61.42 MB
25a | 2019 Offshore Culture Resources Survey Data | 2019-10-30 | 85 KB
25b | Cultural Resources Survey Data Followup | 2019-10-30 | 8.96 MB
25PDFONLY | Cultural Resources Survey Data | 2020-06-08 | 25 KB
27a | RFI 27a: Followup Questions on RFI 027 - Aircraft and Noise | 2018-08-02 | 23 KB
27b | RFI 27b: Additional Transportation Information | 2018-10-05 | 17.31 MB
28a | RFI 28a: Follow-up Questions on RFI 028 - IDF, Freeboard, Precipitation Inputs, and Spillways | 2018-10-05 | 5.05 MB
28b | RFI 28b: Follow-up Questions on RFI 028a - Climate Change Inputs to IDF/Freeboard | 2018-10-05 | 10.35 MB
32a | RFI 32a: Followup Requests on RFI 032 - Conceptual Design and Feasibility Information for Options in March 20, 2018 Technical Note | 2018-08-09 | 3.4 MB
32b | Follow-up request on 32a for GIS polygon data for Proposed Project layout and access route. | 2019-10-30 | 998 KB
34a | RFI 34a: Visual Resource Data | 2018-10-05 | 25.98 MB
34b | RFI 34b: Visual Resource Data | 2018-10-19 | 3.19 MB
34c | RFI 34c: Viewshed for Alternatives | 2018-10-19 | 5.13 MB
34d | Visual Resources Clarification | 2019-10-30 | 15.68 MB
34e | Updated Viewshed Figures | 2020-01-31 | 21.4 MB
34f | Visual Resource Data | 2019-12-11 | 16.02 MB
34g | Updated Viewshed and Simulation | 2020-07-23 | 5.63 MB
39a | Metocean Measurement Program Data | 2019-08-08 | 915 KB
39b | Amakdedori Port Wave Modeling – Data Sources and Input | 2019-12-12 | 4.89 MB
55a | RFI 55a: Follow-up to response to RFI 055 PAG/Pyritic TSF | 2018-10-05 | 127 KB
56a | Final Compensatory Mitigation Plan | 2020-01-31 | 17.42 MB
59a | Additional Throughput Option | 2019-10-30 | 279 KB
62a | Clarification of Cyanide Use in Expanded Mine Scenario | 2019-06-05 | 96 KB
64a | Follow-up to RFI 064 response - Water Quality Criteria | 2019-10-30 | 447 KB
65a | Followup Questions on Summer Only Ferry Operations | 2019-10-30 | 89 KB
66a | Follow-up to RFI 066 Concentrate Pipeline Concept Description | 2019-10-30 | 1.4 MB
66b | Concentrate Pipeline and Water Management | 2020-07-23 | 1.01 MB
68a | RFI 68a: Additional Water Quality Tables | 2018-10-05 | 443 KB
68b | RFI 68b: Additional Water Quality Tables | 2018-10-05 | 168 KB
6a | Followup Questions on Seepage Analysis | 2020-01-31 | 613 KB
6b | Followup on Seepage Analysis | 2019-06-18 | 498 KB
6c | Followup on Seepage Analysis | 2020-01-31 | 1.62 MB
71a | RFI 71a: Followup on RFI 071 Response - Mitigation for Analysis in the EIS | 2018-10-05 | 42 KB
71b | Mitigation for Analysis in the EIS | 2019-10-30 | 976 KB
71c | Update of Avoidance and Minimization Measures in EIS | 2020-05-08 | 261 KB
71d | Additional Avoidance and Minimization Measures Suggested by Cooperating Agencies | 2020-07-23 | 352 KB
75a | Follow-up Questions on Downstream Dam for the Bulk TSF | 2019-10-30 | 4.76 MB
7b | Followup on Air Quality Emission Inventories | 2020-01-31 | 786 KB
82a | Dewatering Impacts to Wetland and Other Waters | 2019-10-30 | 176.83 MB
82b | Followup - Dewatering Impacts to Wetland and Other Waters | 2019-11-20 | 85.46 MB
82c | Indirect Impacts of Dewatering to Wetlands and Other Waters under Mine Expansion | 2020-04-30 | 31.42 MB
84a | Update Construction and Blasting Footprint | 2019-11-13 | 7.56 MB
87a | Water and Sewage Treatment Followup | 2019-07-26 | 107 KB
8a | RFI 8a: Followup on Embankment Stability | 2018-10-05 | 8.21 MB
8b | RFI 8b: Followup on 008/008a Embankment Stability Analyses | 2018-10-05 | 276 KB
8c | RFI 8c: Followup on 008a - Seismic Analyses | 2018-10-05 | 39 KB
8d | Follow-up to response to RFI 008b (Embankment Stability Analysis) | 2019-10-30 | 285 KB
8e | Embankment and Impoundment Summary Table | 2019-10-30 | 646 KB
8f | Follow-up to RFI 008f - Embankment and Impound Summary Table - Cross-Sections | 2019-10-30 | 833 KB
8g | Followup on Seismic Stability Analysis | 2020-01-31 | 14.55 MB
8h | Followup on Seismic Stability Analysis | 2020-01-31 | 325 KB
8i | Pseudo-static Stability Analyses - Other Embankments | 2019-10-30 | 26 KB
8j | Static Stability Analysis, Main WMP | 2019-10-30 | 48 KB
97a | Cultural Resources Surveys for High/Low Potential | 2019-02-06 | 90 KB
97b | Cultural Features in Analysis Area | 2019-02-06 | 241 KB
97c | Subsistence Figures Update Request | 2020-02-06 | 5.8 MB
97d | Updated Subsistence Figures | 2020-07-23 | 6.02 MB
9a | Follow-up to RFI 009 Response: Dispersion and Deposition Modeling | 2019-10-30 | 2.01 MB
9b | Follow-up to Dispersion Modeling - Copper in Dust Deposition | 2019-10-30 | 1.01 MB
9c | Concentrate Transfer to Bulk Carriers | 2019-07-26 | 14 KB
BSEE 1 | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2019-12-30 | 764 KB
BSEE 2 | Cook Inlet Natural Gas Pipeline: Maintenance Schedule | 2019-12-30 | 589 KB
BSEE 3 | Cook Inlet Natural Gas Pipeline: Archaeology Discoveries | 2019-12-30 | 13 KB
BSEE1 | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2020-03-05 | 763 KB
BSEE1a | Cook Inlet Natural Gas Pipeline: Installation Methodology | 2020-04-30 | 18 KB
BSEE2 | Cook Inlet Natural Gas Pipeline: Maintenance Schedule | 2020-03-05 | 589 KB
Title